## TestPlan
Test Planner and Tracker |  |  | g262-01a | The Squad
Test No. ID | Related Systems / User Story | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | R2 beta Outcome (color code cell background) | R2 Outcome (color code cell background)
1 | Registration | System is accessible and configured, registrant is on home page and not logged in | 1. Click registration button. 2. Fill out all forms on page: First name = Boromir, Last name = so Denethor, Username = borofgondor, Email = cap@minastirith.gov, password = faramir, confirmatioin = faramir, phone = 0000000000, Share zone = Minas Tirith 3. Click submit | New user is created.
|  |  | 1. Click registration button. 2. Fill out all forms on page like above, EXCEPT repeat password. 3. Click submit | New user is NOT created. User is presented with error message.
2 | Account Details Modification | Test 1 completed | 1. Click Account Management. 2. Edit Address, enter "Osgiliath 3. Click Save | User’s details are saved to the database and the user is presented with a success message
3 | Tool Deletion | Test 8 completed | 1. Click on owned tool. 2. Click on modify. 3. Click on delete. | Tool is removed from the database and user is presented with a success message
4 | Shed Creation | User is logged in and is not a member of a shed | 1. Click on “Create new shed”. 2. Fill out details form. 3. Click Submit | New shed is added to database.
|  |  | 1. Click on "Create new shed". 2. Enter "Rivendell" in name field. 3. Click submit | New shed is NOT created. User is presented with error message
5 | Tool Borrowing | User is logged in. User has access to a given tool in a local shed | 1. User selects tool other than one he owns. 2. User selects “Request tool” on tool info page. | Acceptance notification and e-mail are sent to owner. User is presented with a confirmation message. Request tool is greyed out for all other users.
6 | User banning | Admin logged in. User has been breaking rules | 1. Admin opens Admin control panel. Admin searches for a username. 2. Admin clicks username. 3. Admin changes status to “Banned”. 4. Admin clicks Save. | User's status is changed to banned in the database. User is presented with a banned message upon login, and then is logged back out.
7 | Category Addition | Admin logged in. Determined that new category is necessary | Admin opens Admin control panel. 2. Admin selects Categories. 3. Admin selects “New”. 4. Admin enters name/ 5. Admin clicks Save. | New category is saved to DB and is available to all users when creating new tool or editing.
8 | Tool creation | User is community shed manager | User opens main shed page. 2. User clicks Add Tool. 3. User fills out details form. 4. User clicks Add | Tool is added to tool list for the shed. Tool is added to the DB.
|  |  | 3. User enters "Anduril" under "Name" and clicks submit | No tool added to DB. User presented with error message
9 | Tool Listing | User is logged in and is a member of a shed | 1. User opens main ToolShed landing page. 2. User selects Borrow Tool. 3. User selects List All Tools | User is presented with a list of all tools.
10 | User banning | Admin logged in. User has been breaking rules | 1. Admin opens Admin control panel. Admin searches for a username. 2. Admin clicks username. 3. Admin changes status to “Banned”. 4. Admin clicks Save. | User's status is changed to banned in the database. User is presented with a banned message upon login, and then is logged back out.
11 | Shed joining | Test 1 completed | 1. Log in as "TaikhoomAttar". 2. Select "Toolsheds". 3. Select "Roy's Shed". 4. Select "Join shed" | TaikhoomAttar is added as a member of Roy's Shed |  | Nothing happens when button pressed
|  |  | 3. Select "Taikhoom's Shed". 4. Select "Join shed" | User is presented with a message saying they can't join their own shed |  | Nothing happens when button pressed
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Instructions
Test plan Instructions
It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests
Test No. | User Story covered | Preconditions | Test Description | Expected Outcome | R1 Outcome | R2 Outcome
1 | Move Player | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester1 | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located at Reading Railroad cell.
2 | Move Player | Test 1 completed | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located on Jail cell.
3 | Move Players in Turns | Game is in test mode. Game is in initial state. Number of Players: 2 Player 1 Name: Tester1 Player 2 Name: Tester2 | Player 1 Dice Roll: 5 Player 1 End Turn | Player 1 is located at Reading Railroad
|  |  | Player 2 Dice Roll: 3 Player 2 End Turn | Player 2 is located at Baltic Avenue
4 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 39 Player 1 End Turn | Player 1 is located at Boardwalk
|  |  | Verify Player 1 bank balance | Player 1 has $1500
5 | Pass Go | Game is in test mode Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 40 Player 1 End Turn | Player 1 is located on GO cell
|  |  | Verify Player 1 bank balance | Player 1 has $1700 | Go money paid out only after passing GO, not when it is reached.
6 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 41 Player 1 End Turn | Player 1 is located at Mediterranean Avenue
|  |  | Verify Player 1 bank balance | Player 1 has $1700